## Components-by-priority
Status: | 02/02/2017; 14:00 | * for all device it must be enabled to pass through beam: vacuum functional and beam path free
Completion dates
Tunnel/ section | Device | Priority* | coor. person | Mechanics by/when | Cables, Elec-HW, Doc by/when | Beckhoff fw by AE/when | Ctrl-sw by CAS/when | Techn. comm. by/when | Comments
XTD2 | General vacuum | High | Dommach | done | VG/done | done (C) |  |  | C: XGM not yet fully
XTD2 | Absorder & V0 | High | Dommach | ? | VG/? (C) |  |  |  | Waiting for WG-19 (VG to find out)
XTD2 | Fast valve | High | Dommach | done | VG/done | wk4
XTD9-SPB | Fast valve | High | Dommach | done | VG/done | wk4
XTD9-FXE | Fast valve | High | Dommach | done | VG/done | wk4
XTD2 | Diff. pumping | High | Villanueva | done | VG/done | done
XTD2 | Diff. pumping | High | Villanueva | done | VG/done | done
XTD9 | General vacuum | High | Dommach | ? | VG/wk5 | wk4/5
XTD2 | Imager (SR) | High | Koch | done | 74/? | wk5
XTD2 | Imager (FEL) | High | Koch | done | ok, except trigger | ok for local tests Beckhoff loop wk5
XTD2 | Imager | High | Koch | done | ok, except trigger | ok for local tests Beckhoff loop wk5
XTD9 | Imager | High | Koch | done | ok, except trigger | ok for local tests Beckhoff loop wk5
XTD9-SPB | Imager | High | Koch | done | ok, except trigger | ok for local tests Beckhoff loop wk5
XTD9-FXE | Imager | High | Koch | done | ok, except trigger | ok for local tests Beckhoff loop wk5
XTD2 | PSLIT | High | Sinn | done (C) | VG/? (C) | wk5 |  |  | LDVDT encoders: medium priority; MKK: water conection
XTD9-SPB | PBLM | High | Sinn | ? | VG/wk4 | wk9
XTD9-FXE | PBLM | High | Sinn | ? | VG/wk4 | wk9
XTD2 | XGM | High | Grünert | done (?) | cables wk4, vac Beck wk6 | wk6 | DESY (Doocs)
XTD2 | Solid attenuator | High | Sinn | done | VG/done (C) | wk5 |  |  | Thermo-elements: medium priority
XTD2+9 | EPS system | High | Sinn | n.a. | VG/? | wk6
XTD2 | Mirror (1st) | High | Sinn | done | VG/done (C) | wk5 |  |  | Piezo & sim. movement: low priority
XTD2 | Mirror (2nd) | High | Sinn | wk5 | VG/done (C) | wk5 |  |  | Piezo & sim. movement: low priority
XTD2 | Beam shutter | High | Dommach | done | VG/? (C) | wk8 |  |  | needs preparatory work by Wp-38
XTD9 | Mirror (Dist.) | High | Sinn | done | VG/done | wk5 |  |  | Piezo & sim. movement: low priority
XTD9-SPB | FE/Beam shutter | High | Dommach | done | VG/? (C) | wk8 |  |  | needs preparatory work by Wp-38
XTD9-FXE | FE/Beam shutter | High | Dommach | done | VG/? (C) | wk8 |  |  | needs preparatory work by Wp-38
XTD2 | K-Mono | Medium | Freund | done | 74/ | wk10
XTD2 | CRL | Medium | Batchelor | wk3 |  | wk11
XTD2 | PBLM | Medium | Sinn | ? | VG/ | wk9
XTD2 | MCP | Medium | Grünert | done | 74/ | wk10
XTD9 | Hirex (GU & CU) | Medium | Grünert | wk3 | 74/ | wk12
XTD9 | PBLM | Medium | Sinn | ? | VG/ | wk9
XTD9-SPB | Diff. pumping | Medium | Villanueva | done | VG/wk5 | wk11
XTD9-SPB | XGM | Medium | Grünert | wk3 (?) | cables wk5, vac Beck wk7 | wk11 | DESY (Doocs)
XTD9-SPB | Diff. pumping | Medium | Villanueva | done | VG/wk5 | wk11
XTD9-SPB | CRL | Medium | Weinhausen | done | 84/wk6 | wk13
XTD9-FXE | Mono (2 chambers) | Medium | Sinn | wk5 | VG/
XTD9-SPB | Pulse picker | Low | Weinhausen | done | 84/ | wk13
XTD9-SPB | Attenuator | Low | Weinhausen | done | 84/wk6