## Components-by-priority
| Status: | 10/03/2017; 11:30 |  |  | * for all device it must be enabled to pass through beam: vacuum functional and beam path free
Completion dates
| Tunnel/ section | Components | Comp-name | Loop | Priority* | coor. person | Mechanics by/when | Cables, Elec-HW, Doc by/when | Beckhoff fw by AE/when | Ctrl-sw by CAS/when | Techn. comm. by/when | Comments
| XTD2 | General vacuum |  |  | High | Dommach | done | VG/done | done | wk11 |  | Karabo running but still a lot of undefined and error states
| XTD2 | Absorder & V0 |  |  | High | Dommach | done | VG/??, WP19/?? | ?? | ?? |  | Waiting for WG-19 and a cable still needs to be pulled for reading back the state
| XTD2 | Fast valve |  |  | High | Dommach | done | VG/done | done | wk11
| XTD9-SPB | Fast valve |  |  | High | Dommach | done | VG/done | done | wk11
| XTD9-FXE | Fast valve |  |  | High | Dommach | done | VG/done | done | wk11
| XTD2 | Diff. pumping |  |  | High | Villanueva | done | VG/done | done | wk11
| XTD2 | Diff. pumping |  |  | High | Villanueva | done | VG/done | done | wk11
| XTD9 | General vacuum |  |  | High | Dommach | done | VG/done | done | done
| XTD2 | Imager (SR) |  |  | High | Koch | done | WP74/done | done | done
| XTD2 | Imager (FEL) |  |  | High | Koch | done | WP74/done | done | done
| XTD2 | Imager |  |  | High | Koch | done | WP74/done | done | done | started
| XTD9 | Imager |  |  | High | Koch | done | WP74/done | done | done
| XTD9-SPB | Imager |  |  | High | Koch | done | WP74/done | done | done
| XTD9-FXE | Imager |  |  | High | Koch | done | WP74/done | done | done
wk12 | XTD2 | PSLIT |  |  | High | Sinn | done (C) | done | done | wk12 |  | LDVDT encoders: medium priority; MKK: water conection
| XTD9-SPB | PBLM |  |  | High | Sinn | done | done | wk11 | wk11
| XTD9-FXE | PBLM |  |  | High | Sinn | done | done | wk11 | wk11
| XTD2 | XGM |  |  | High | Grünert | done | wk11 | wk11 | DESY (Doocs) |  | Cables were not connected differently than stated last week and problems with defining interlock
| XTD2 | Solid attenuator |  |  | High | Sinn | done | done | done | wk11 |  | Thermo-elements: medium priority
| XTD2+9 | EPS system |  |  | High | Sinn | n.a. | wk11 | wk11 | wk11 |  | Missing bus couplers finally arrived in wk 10
| XTD2 | Mirror (1st) |  |  | High | Sinn | done | VG/done (C) | done | done |  | Piezo & sim. movement: low priority
| XTD2 | Mirror (2nd) |  |  | High | Sinn | done | VG/done (C) | done | done |  | Piezo & sim. movement: low priority
| XTD2 | Beam shutter |  |  | High | Dommach | done | VG/??, WP19/?? | ?? | ?? |  | Waiting for WG-19 and a cable still needs to be pulled for reading back the state
| XTD9 | Mirror (Dist.) |  |  | High | Sinn | done | VG/done | done | done |  | Piezo & sim. movement: low priority
| XTD9-SPB | Diff. pumping |  |  | Medium | Villanueva | done | done | wk11 | wk11
| XTD9-SPB | XGM |  |  | Medium | Grünert | done | wk11 | wk11 | DESY (Doocs) |  | Cables were not connected differently than stated last week and problems with defining interlock
| XTD9-SPB | Diff. pumping |  |  | Medium | Villanueva | done | done | wk11 | wk11
| XTD9-SPB | FE/Beam shutter |  |  | High | Dommach | done | VG/??, WP19/?? | ?? | ?? |  | Waiting for WG-19 and a cable still needs to be pulled for reading back the state
| XTD9-FXE | FE/Beam shutter |  |  | High | Dommach | done | VG/??, WP19/?? | ?? | ?? |  | Waiting for WG-19 and a cable still needs to be pulled for reading back the state
| XHEXP | enable S1 PP laser | n.a. | n.a. | High | Lederer | [5 empty] | need analysis by AE, CAS, OL-group about resource need
| XHEXP | enable S1 det. Tests | n.a. | n.a. | High | Kuster | [5 empty] | need analysis by AE, CAS, OL-group about resource need
| XHEXP-FXE | Vacuum system | FXE_OGT1_VAC | _loop1 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Motion | _OGT1_MOV | _loop1 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Beam Imaging U | _OGT1_BIU | _loop1 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Spectrum Ana. | _OGT1_SA | _loop1 | Low | Galler | [5 empty] | not needed for 1st beam
| XHEXP-FXE | PSLIT | _OGT1_PSLIT | _loop1 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Int. Pos. Monitor | _OGT1_IPM | _loop2 | Low | Galler | [5 empty] | not needed for 1st beam
| XHEXP-FXE | Time Arr. Det. | _OGT1_TAD | _loop2 | Low | Galler | [5 empty] | not needed for 1st beam
| XHEXP-FXE | Attenuator | _OGT1_ATT | _loop2 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Vacuum system | _OGT2_VAC | _loop2 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Motion | _OGT2_MOV | _loop2 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | Beam Imaging U | _OGT2_BIU-1 | _loop2 | High | Galler | wk10 | wk10 | wk11 | wk12
| XHEXP-FXE | CRLs | _OGT2_CRL | _loop3 | High | Galler
| XHEXP-FXE | PSLIT | _OGT2_PSLIT | _loop3 | High | Galler
| XHEXP-FXE | Beam Imaging U | _OGT2_BIU-2 | _loop4 | High | Galler
| XHEXP-FXE | Motion | _SMS_MOV | _loop4 | High | Galler
| XHEXP-FXE | Clean-up slits | _AUXT_CSLIT | _loop4 | High | Galler
| XHEXP-FXE | Motion | _DET_MOV | _loop4 | High | Galler
| XHEXP-FXE | Johann Spectro. | _SMS_JSS | _loop5 | High | Galler
| XHEXP-FXE | vHamos Spectro. | _SMS_VHS | _loop7 | High | Galler
| XHEXP-FXE | Beam Imaging U | _OGT3_BIU | _loop8 | Low | Galler
| XHEXP-FXE | Spectrum Ana. | _OGT3_SA | _loop8 | Low | Galler
| XHEXP-FXE | Int. Pos. Monitor | _OGT3_IPM | _loop8 | Low | Galler
| XHEXP-FXE | Motion | _OGT3_MOV | _loop8 | Low | Galler
| XHEXP-SPB-OPT | Vacuum system | SPB_MKB_VAC | SPB-01:8 | High | Bean | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Alignment laser | _MKB_ALAS | SPB-01:1,2 | High | Sato | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | PSLIT | _MKB_PSLIT | SPB-01:3 | High | Batchelor | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Screen | _MKB_SCR‐1 | SPB-01:1,2 | High | Giewekemeyer | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Vacuum system | _OHD_VAC | SPB-02:3 | High | Bean | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Vacuum system | _TRN_VAC | SPB-02:3 | High | Bean | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Clean-up slits | _OHD_CSLIT | SPB-02:1 | Low | Stern | [5 empty] | not needed for 1st beam
| XHEXP-SPB-OPT | Screen | _OHD_SCR | SPB-02:2 | High | Giewekemeyer | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-OPT | Shutter | _OHD_SHUT | SPB-02 | High | Weinhausen | wk12 | wk12 | wk13 | wk14
| XHEXP-SPB-EXP | Alignment laser | _EHU_ALAS | SPB-03:1,2 | High | Sato
| XHEXP-SPB-EXP | Screen | _EHU_SCR | SPB-03:1 | High | Giewekemeyer
| XHEXP-SPB-EXP | Vacuum system | _EHU_VAC | SPB-03:6 | High | Bean
| XHEXP-SPB-EXP | Clean-up slits | _NKB_CSLIT-1 | SPB-04:1 | High | Stern
| XHEXP-SPB-EXP | Clean-up slits | _NKB_CSLIT-2 | SPB-04:2 | High | Stern
| XHEXP-SPB-EXP | Screen | _NKB_SCR | SPB-04:3 | High | Giewekemeyer
| XHEXP-SPB-EXP | Vacuum system | _NKB_VAC | SPB-04:6 | High | Bean
| XHEXP-SPB-EXP | DPS | _IRU_DPA | ??? | High | Messerschmidt
| XHEXP-SPB-EXP | IL Microscope | _IRU_INLINEMIC | ??? | High | Sikorski
| XHEXP-SPB_EXP | Injector man. | _IRU_INJ-MOV | ??? | High | Sikorski
| XHEXP-SPB-EXP | Fixed target mot | _IRU_FIXTARGET | ??? | High | Sikorski
| XHEXP-SPB-EXP | Vacuum system | _IRU_VAC | SPB‐05 | High | Bean
| XHEXP-SPB-EXP | AGIPD-z-move | _IRU_AGIPD1M… | ??? | High | Sikorski
| XHEXP-SPB-EXP | L. detector chill | _IRU_CHL | SPB‐05 | High | Sikorski
| XHEXP-SPB-EXP | AGIPD-controls | _IRU_AGIPD1M | SPB-06 | High | Sikorski
| XHEXP-SPB-EXP | Comp Supp Struct | _EHC_CSS | SPB-07 | High | Bean
| XHEXP-SPB-EXP | Vacuum system | _EHC_VAC | SPB-07 | High | Bean
| XHEXP-SPB-EXP | Screen | _EHC_SCR-1 | SPB-07 | High | Giewekemeyer
| XHEXP-SPB-EXP | Beam stop | _EHD_IBS | SPB-08 | High | Weinhausen
| XHEXP | SASE1 PP laser |  |  | High | Lederer
| XHEXP | SASE1 detector tests |  |  | High
| XTD2 | K-Mono |  |  | Medium | Freund | done | WP74/done | wk12
| XTD2 | CRL |  |  | Medium | Batchelor | done |  | wk13 |  |  | alignment expected in week 7 or 8
| XTD2 | PBLM |  |  | Medium | Sinn | done | VG/ | wk12
| XTD2 | MCP |  |  | Medium | Grünert | done | WP74/done | wk13
| XTD9 | Hirex (GU & CU) |  |  | Medium | Grünert | done | WP74/done | wk12
| XTD9 | PBLM |  |  | Medium | Sinn | done | VG/ | wk12
| XTD9-SPB | CRL |  |  | Medium | Weinhausen | done | 84/wk6 | wk13
| XTD9-FXE | Mono (2 chambers) |  |  | Medium | Sinn | done | VG/ | wk4
| XTD9-SPB | Pulse picker |  |  | Low | Weinhausen | done | 84/ | wk13
| XTD9-SPB | Attenuator |  |  | Low | Weinhausen | done | 84/wk6 | wk13
| XTD9-SPB | Diagnostic Screen |  |  | Low | Weinhausen |  |  | wk13