## Components-by-priority
Status: | 1/06/2017; 15:00
Completion dates
FXE/LPD1M | Device | Priority* | Coor. Person | Mechanics by/when | Cables, Elec-HW, Doc by/when | Beckhoff fw by AE/when | Ctrl-sw by CAS/when | SW by WP75 Side/when | Techn. comm. by WP75 by/when | Comments Assumption Exclusive Implementation (AGIPD or LPD)
HERA South | AGIPD/Cooling System |  | Sztuk-Dambietz | Done | Done | Done | Done | Done | Done
HERA South | AGIPD/Vacuum System | High | Sztuk-Dambietz | Done | Done | Done | Done | w27 | w27 | Macros for pumping and venting need to be implemented and tested. Not critical.
HERA South | AGIPD/Cables + Power Supplies | High | Sztuk-Dambietz | Done | Done | Done | Done | w26 | w26 | Frist version of power procedure implemented and tested at HERA South. Some problems were discovered. The procedure has to be retested after bug fix. No manpower in WP75 was available to look at the issue this week. Not critical for operation of the detector at the moment, requried for beam line.
HERA South | AGIPD/Detector Control System | High | Hauf | Not Applicable | Done | Not Applicable | w25 | w25 | w25 | Tests of updated (after the AGIPD squad) MFPGA and MC control software done to the level which does not require full DAQ system. Control system is operational. Basic test GUI for operation of the detector available. Problem with memory leak for MFPGA was observed and reported to CAS.
HERA South | AGIPD/Detector Safety System | High | Sztuk-Dambietz | Not Applicable | Done | w24/w25 | w25 | w25 | w25 | Beckhoff related (AE): Interlock system is operational as specified. Additional saftey features need to be implemented, but are not critical for safety of the system. AE is informed and should fix the remaining issues next week. CAS/WP-75 related: First version of middle layer devices exists, but is not fully functional yet. CAS is informed about the problem.
HERA South | AGIPD/Quadrant Motion System |  | Sztuk-Dambietz | Not Applicable
HERA South | AGIPD/Clock & Control System | High | AE | Not Applicable | Done | Not Applicable | Done | ?? | ?? | The same as for LPD. The C&C device have to be installed on AGIPD Control PC
HERA South | AGIPD/Alignment | Low | Hauf | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w27 | Tech. comm. depends on availability of X-ray beam at beam line
HERA South | AGIPD/DAQ and Data management | High | ITDM | Not Applicable | Done | Not Applicable | Done | w25 | w25 | Wiring of TB to PC layer was done. Configuration of PC layer and 1Mpix TB for AGIPD has to be done by ITDM(WP-75)/AE respectively.
HERA South | AGIPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | w25 | w25 | If no changes are made on CAS side Ctr-sw part done, otherwise upgrade on WP75 side required; Software for AGIPD needs to be ported to XFEL library. Time line adjusted to LPD priority
HERA South | AGIPD/Performance without X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | Done | w26 | w27 | Algorithms exist, macro implementation + definition outstanding
HERA South | AGIPD/Performance with X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | Done | w28 | w29
HERA South | LPD/Cooling System |  | Lang | Done | Done | Not Applicable | Not Applicable | Not Applicable | Done
HERA South | LPD/Cables + Power Supplies |  | Lang | Not Applicable | Done | Not Applicable | Done | Done | Done
HERA South | LPD/Detector Control System |  | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | Done | Done
HERA South | LPD/Detector Safety System |  | Lang | Not Applicable | Done | Not Applicable | Not Applicable | Not Applicable | Done
HERA South | LPD/Quadrant Motion System |  | Lang | Done | Done | Not Applicable | Done | Not Applicable | Done
HERA South | LPD/Clock & Control System |  | AE | Not Applicable | Done | Not Applicable |  | Done | Done | Potentially user-friendly middle layer device needed on top
HERA South | LPD/Alignment | Low | Lang | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w25 | Tech. Comm. Depends on availabiltiy of X-ray beam at beam line, photographic technique making good progress - tested on quadrant system
HERA South | LPD/DAQ and Datamanagement | High | ITDM | Not Applicable | Done | Not Applicable | Done | Done | w24 | More stable results bypassing trainbuilder, reader service not yet ready by ITDM, no metadata catalogue
HERA South | LPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | Done | w23
HERA South | LPD/Performance without X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | Done | Done | w25 | Algorithms exist, additional macros to be implemented + definition outstanding
HERA South | LPD/Performance with X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | Done | Done | w24 | X-ray tests will be shortened to one week to check basic functionality and comparison with charge injection data
HERA South | Train Builder Device | High | AE | Not Applicable | Req.Doc. Done | Not Applicable | w25 | w25 | w25 | Trainbuilder is operational, first iteration for Karabo device delivered to CAS, but needs updates/improvements